Proof of Concept

Automatic Court Detection & Reliable Bounce Calls

Pickleball line-calling from a single phone, placed anywhere

Timeline:  10 working days (hard cap)        Date:  June 2026

Data available:  4 courts (multi-angle, multi-lighting)        Primary gate:  auto court-detection works under occlusion

# 1. What this POC must prove

This is a from-scratch proof of concept. No prior result is assumed to carry over — earlier work is treated as a starting reference only, not as a solved component. The POC succeeds or fails on two independent claims, each with a measurable exit gate.

Claim A (primary). A phone placed anywhere around the court can recover the court geometry automatically, in under ten seconds, even when the net, players, shadows, or a missing far baseline hide parts of the lines. No human dragging or clicking.

Claim B (supporting). The system calls bounces IN / OUT correctly at least 80% of the time on real rallies. The current baseline is 68%; this POC must close that 12-point gap and show why it closed, not just that a number moved.

Honest non-goal. A single low camera cannot perfectly distinguish a ball contacting the line from a ball passing over it at ankle height. This POC does not claim to eliminate that ambiguity; it scopes around it and states where it bites.

## Success gates at a glance

| Track | What is built | Exit gate (pass/fail) |
| --- | --- | --- |
| A — Court | Two auto-detection methods built, then a bake-off picks one | Calibrates in <10s; correct under net + people + missing far baseline |
| B — Bounce | Diagnose the 68% baseline, fix the dominant error source, re-measure | ≥ 80% correct IN/OUT calls on a held-out rally set |

Why diagnose before building (Track B). 32% of calls are currently wrong, and the cause is unknown. Jumping straight to a heavier model — e.g. full 3D triangulation — without knowing the error mix is how a team spends ten days and lands at 71%. The first move is to find out where the errors live.

# 2. Track A — Automatic court detection under occlusion

## The problem, stated precisely

The court must be located from a single frame with zero user interaction. Three things break naive approaches, and all three can occur at once:

- The net mesh blurs the far baseline; through it, that line is often unrecoverable as a sharp edge.

- Mounting a phone high enough (≈7 ft) to see the far end cleanly is a usability dealbreaker — players will not set that up.

- Portable nets have wheeled bases that sit off the court lines, so net posts are NOT at known court coordinates and cannot anchor calibration.

- Players, paddles, and bags occlude arbitrary stretches of line during real use, so no single line is guaranteed fully visible.

The core idea. Do not depend on any one line being whole. Fit the entire rigid court template (the known 20 ft × 44 ft layout) to whatever painted evidence is visible, so the global shape constrains the parts that are hidden. Occlusion tolerance comes from matching the whole pattern, not from trusting individual lines.

## Two candidate methods — build both, then bake off

The method choice is not obvious in advance, so the POC prototypes both on the same data and commits to the winner on day 7. Both output the same thing: a homography mapping court feet to image pixels, plus a confidence/error score.

| Method | How it works | Bet / risk |
| --- | --- | --- |
| Segmentation + template fit | A small net segments every white-line pixel; RANSAC fits the rigid 20×44 template to the mask and solves the homography. | Strong occlusion tolerance (whole layout matched). Risk: messy masks on low-contrast / glare surfaces. |
| Keypoint regression | A net regresses court line-intersections directly in pixel space — including occluded ones — like human-pose estimation. Points feed the homography. | Clean, direct, fast. Risk: must learn to hallucinate hidden points plausibly; needs good keypoint labels. |

Bake-off criteria (day 7). Decided on three numbers measured on a held-out court: (1) median reprojection error in court feet, (2) success rate under heavy occlusion, (3) wall-clock time per frame. Highest occlusion-robust accuracy within the <10s budget wins; the loser is dropped.

## Why this is phone-agnostic

A homography is a set of point correspondences plus a focal estimate recovered from the court itself — no LiDAR, no depth sensor, no iPhone-specific pipeline. Any 1080p60 camera, Android or iOS, supplies enough spatial resolution to fit lines. This is a deliberate divergence from tools that mandate a specific phone and a tall tripod: the cost is needing a trained detector, which is exactly what the 4-court dataset is for.

# 3. Track B — From 68% to 80% correct calls

The target is concrete and external: the reviewers want ≥ 80% correct bounce calls. The last measured result was 68%. This track is structured as an accuracy investigation, not a feature build.

## Step 1 (Days 1–2): Diagnose the 68%

Collect every wrong call on the existing test footage and label its root cause. A call can be wrong for reasons that live in completely different parts of the pipeline, and the fix differs entirely by cause:

| Failure category | What it looks like | Lives in |
| --- | --- | --- |
| Missed / phantom bounce | Ball bounced but no call (or a call with no bounce) | Detector / event logic |
| Ground vs. fly-over | Called a bounce when ball passed over the line in the air | Camera height / 3D |
| Right bounce, wrong side | Bounce found, but IN/OUT verdict wrong near the line | Calibration accuracy |
| Timing / wrong frame | Bounce located a few frames off, shifting its court position | Tracking / temporal |

Output of Step 1: a histogram of the 32% errors by category. This single chart decides where the next four days go. We do not guess the dominant cause here — we measure it.

## Step 2 (Days 3–4): Target the dominant cause

The fix is chosen by the histogram, not in advance. The likely branches:

- If “ground vs. fly-over” dominates: recover ball height. Either a second calibrated camera (triangulate true z) or a learned monocular height cue. This is the deepest fix and the one most likely to lift a hard ceiling.

- If “wrong side near the line” dominates: the bounce is fine; calibration precision is the problem. Tighten the court fit (this is where Track A directly helps Track B) and the verdict sharpens with no detector change.

- If “missed / phantom” dominates: strengthen the bounce event model — a trajectory-physics fit or a learned spatio-temporal classifier — rather than a hand-tuned pixel-minimum rule.

- If “timing” dominates: improve sub-frame bounce localization; small temporal error becomes large court-position error for a fast ball.

## Step 3 (Days 5–8): Fix and re-measure, on a loop

Implement the targeted fix, re-run against the same labeled ground-truth set, and read the new accuracy. Iterate while days remain. The 80% gate is checked on a held-out set the fix was not tuned on, so the number is honest rather than overfit.

Stretch realism. If the dominant cause turns out to be ground-vs-fly-over, hitting 80% in this window may require the second camera. The POC will say so plainly rather than claim a monocular fix it cannot defend.

# 4. The 10-day plan

Two tracks run in parallel through day 8, then converge. Data capture is shared and front-loaded — it feeds both tracks.

| Days | Track A — Court | Track B — Bounce |
| --- | --- | --- |
| 1–2 | Capture & label 4 courts (angles, lighting); define held-out set | Diagnose the 68%: categorize every wrong call → error histogram |
| 3–4 | Build Method 1 (segmentation + template fit) | Pick & start the fix targeting the dominant error cause |
| 5–6 | Build Method 2 (keypoint regression) | Implement fix; first re-measurement vs. ground truth |
| 7 | Bake-off: accuracy × occlusion × speed → keep the winner | Iterate fix; second re-measurement |
| 8 | Harden winner on occluded / glare frames | Lock accuracy number on held-out set |
| 9–10 | Integrate • demo on a held-out court • write up results & honest limits (both tracks) | ← |

## Deliverables on day 10

- A demo: phone placed at a fresh court → court auto-detected in <10s, overlaid correctly despite net/people.

- A one-page accuracy report for bounce calls: baseline 68%, final number, and the error histogram that explains the change.

- A go / no-go recommendation per track, with the specific blocker if a gate was missed.

# 5. Risks & honest caveats

| Risk | Impact | Mitigation |
| --- | --- | --- |
| 4 courts overfit the detector | Court detection fails on unseen surfaces/colors | Heavy augmentation; reserve 1 court fully held-out; report cross-court accuracy |
| 10 days too short to train from scratch | Detector underperforms the gate | Start from a pretrained backbone; fine-tune, don't train from zero |
| 80% needs true 3D (2nd camera) | Monocular fix can't reach the gate | Diagnose first; if so, state it and scope the 2-camera path explicitly |
| Ground-vs-fly-over ambiguity | Persistent near-line errors from one low camera | Named as a non-goal; quantify its share of remaining error |

Bottom line: Track A is the centerpiece and is judged purely on occlusion-robust auto-detection under 10 seconds. Track B is judged on one honest number — ≥ 80% correct calls — reached by diagnosis, not guesswork. Anything not proven by day 10 is reported as such.